## Public Facing Report
SMP Reference | Area | Location | Complaint Description | Town Village | Received | Acknowledged | Suitable for SCV | Date sent to NYFRS | Date sent back to Highways 60mph | Collisions all | Collisions speed related | Existing speed limit | Speed survery dates | Mean Speed | ID85 | Date sent to RSTG | RSTG Decision | Date Cust Decision Letter Sent
CR1510010 | CRAVEN | Skipton Road | Embsay | Embsay | 23/03/2015 | 16/04/2015 |  | 14/04/15 then 02/12/2015 Redployment requested | N/A | 0 | 0 | 30
CR1510020 | CRAVEN | B6265 from Skipton | Hewittgate. Near junction of Main Street & Old Village of Threshfield | Threshfield | 07/04/2015 | 16/04/2015 | AWAITING SITE REVIEW | Redeployment 27/01/2016 | N/A | 15 Slight/1 Serious | 3 Slight | 30 | 22/02/2016 - 29/02/2016 | 33/31 | 37/36 | 01/03/2016 | ENFORCEMENT | 18/03/2016
CR1510030 | CRAVEN | West Lane | Embsay | Embsay | 28/04/2015 | 29/04/2015 | N/A | 16/01/2016 | N/A | 0 | 0 | 30 | 25/02/16 - 02/03/16 | 20 | 26/25 | 08/03/2016 | NFA | 10/03/2016 by KM
CR1510040 | CRAVEN | Brackenley Lane | Embsay | Embsay | 29/04/2015 | 30/04/2015 | N/A | 21/01/2016 | N/A | 0 | 0 | 30 | 01/02/16 - 08/02/16 | 26/23 | 32/31 | 09/02/2016 | NFA | 11/02/2016
CR1510050 | CRAVEN | Marton Road | Gargrave | Gargrave | 11/05/2015 | 12/05/2015 | N/A | 21/01/2016 | N/A | 2 Slight | 1 Slight | 30 | 30/11/2015-08/12/2015 | 20/26 | 27/32 | 25/01/2016 | NFA | 04/02/2016
CR1510060 | CRAVEN | A56 ( Not B6265 AS ON THE LETTER!) Church Road | Thornton in Craven (Just inside 30 mph) | Oakworth, Keighley | 01/06/2015 | 02/06/2015 |  | 21/01/2016 | N/A | 3 ( 2 slight and 1 Serious) | 1 Serious | 30 | Redploy request 04/02/16 Multi data sets
CR1510061 | CRAVEN | B6265 | Through Cracoe Village | Cracoe | 17/06/2015 | 18/06/2015 | AWAITING SITE REVIEW | 21/01/2016 | N/A | 1 Serious | 0 | 40 |  | 39/41 | 47/47 | 22/01/2016 | Matrix/Enforcement | 04/02/2016
CR1510070 | CRAVEN | Appletreewick | Appletreewick, Skipton | Appletreewick | 13/07/2015 | 14/07/2015 | N/A | 21/01/2016 | N/A | 1 serious | 0 | 30 | 25/01/2016-01/02/2016 | 24/20 | 30/28 | 04/02/2016 | NFA | 09/02/2016
CR1510080 | CRAVEN | Graystonber Lane | Austwick | Clapham | 28/07/2015 | 29/07/2015 |  | 08/12/2015 | N/A | 0 | 0 | 30
CR1510090 | CRAVEN | A687 by Beck Cottage | Beck Cottage, Burton in Lonsdale | Burton in Lonsdale | 01/10/2015 | 06/10/2015 | AWAITING SITE REVIEW | 21/01/2016 | N/A | 0 | 0 | 30 | 09/02/16-17/02/16 | 36/35 - 32/31 | 41/41 - 37/37 | 23/02/2016 | ENFORCEMENT | 10/03/2016 by KM
CR1510100 | CRAVEN | Greatwood Avenue | Outside 72 Greatwood Avenue | Skipton | 15/11/2015 | 15/11/2015 |  | 09/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510110 | CRAVEN | East Lane | Train Station to the Post office. 8-9am and 4-7pm | Embsay, Skipton | 17/11/2015 | 17/11/2015 |  | 08/12/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510120 | CRAVEN | School Lane | Junction of Maypole Green and School Lane and Green Lane | Long Preston, Skipton | 16/11/2015 | 16/11/2015 |  | 08/12/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510130 | CRAVEN | Main Street | Between Kirk Lane and The Elm Tree | Embsay | 17/11/2015 | 17/11/2015 | N/A | 09/02/2016 | N/A | 1 Serious ( not speed related) | 0 | 30 | 02/03/2016 - 09/03/2016 | 25/27 | 30/32 | 11/03/2016 | NFA | 16/03/2016
CR1510140 | CRAVEN | Eshton Road | From and to the A65. Near Rowan House, Gargrave | Gargrave, Skipton | 19/11/2015 | 20/11/2015 |  | 09/02/2016 Redeployment requested 05/05/16 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510150 | CRAVEN | Bannister Walk | Outside 4 Bannister Walk, Cowling | Cowling | 26/11/2015 | 26/11/2015 | N/A | 09/02/2016 | N/A | 0 | 0 | 30 | 30/03/2016 - 13/04/2016 | 15/16 | 19/19 | 03/05/2016 | NFA | 04/05/2016
CR1510160 | CRAVEN | B6479 Horton in Ribbersdale | Close to the Village Pirmary School and Golden Lion Hotel | Horton in Ribblesdale | 04/12/2015 | 07/12/2015 |  | 09/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510170 | CRAVEN | A65 Hellifield Road | Canal Bridge to 60 High Street, Gargrave | West Street, Gargrave, Skipton | 04/12/2015 | 07/12/2015 | N/A | 09/02/2016 | N/A | 2 Slight | 0 | 30 | 17/03/16-23/03/16 | 30/28 | 34/33 | 20-04-16 | MATRIX | 04/05/2016
CR1510180 | CRAVEN | Church Street | A65 junction to Railway Station, Gargrave | Gargrave, Skipton | 16/12/2015 | 16/12/2015 |  | 09/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
CR1510210 | CRAVEN | A65 Draughton bypass | Junctions from A65 into Draughton | Draughton, Skipton | 22/12/2015 | 22/12/2015 | N/A | N/A | 21/04/16 | 1 Slight/1 Serious/1 Fatal | 0 | 60 |  |  |  |  | 60-Back to Highways
CR1510220 | CRAVEN | B6265 | Through Hebden Village | Skipton | 12/01/2016 | 15/01/2016 |  | 09/02/2016 | N/A | 3 slight | 0 | 40 | 29/02/16 - 07/03/16 | 40/39 | 48/48 | 08/03/2016
CR1610200 | CRAVEN | Park Road | From junction at Wheatlands Lane towards Lothersdale Road | Cross Hills | 27/01/2016 | 29/01/2016 | N/A | 09/02/2016 | N/A | 0 | 0 | 30 | 24/03/2016 - 01/04/2016 | 30/30 | 35/36 | 28/04/2016 | MATRIX | 04/05/2016
CR1610230 | CRAVEN | A65 | Long Preston Village | Clapham, Lancaster | 27/01/2016 | 27/01/2016 |  | 09/02/2016 | N/A | 3 Slight ( not speed related) | 0 | 30
CR1610240 | CRAVEN | Low Demesne | From Ingleton Primary School up to Manor Close | Ingleton | 05/02/2016 | 05/02/2016 |  | 24/02/2016 | N/A | 0 | 0 | 30
CR1610250 | CRAVEN | Carleton Road | Whole road from Keighley Road junction | Skipton | 07/02/2016 | 08/02/2016 |  | 08/03/2016 | N/A | 1 | 0 | 30 |  |  |  |  | TBC
CR1610260 | CRAVEN | A65 Through Conison Cold | From the Aire bridge to the top of the hill | Skipton | 18/02/2016 | 24/02/2016 |  |  | N/A | 3 slight (2 speed related) | 2 slight | 40 from the bridge up to 30 as you come to the village
CR1610270 | CRAVEN | B6160. Main Street, Burnsall | Both ways coming into the village | Burnsall | 21/03/2016 | 22/03/2016 |  | 21/04/2016 | N/A | 0 | 0 | 30 in the village
HB1510010 | HAMB | Main street A19 | Shipton by Beningbrough | Shipton by Beningbrough | 08/07/2015 | 06/08/2015 | YES - SUSPENDED | 21/01/2016 - Redployment requested 25/04/16 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
HB1510020 | HAMB | Coombs Close | T Junction of Coombs Close & Huby Road, Sutton on the Forest | Sutton on the Forest | 03/07/2015 | 06/08/2015 | N/A | 16/12/2015 | N/A | 0 | 0 | 30 | 30/11/2015 - 07/12/2015 | 29/28 | 34/33 | 16/12/2015 | NFA | 12/02/2016
HB1510030 | HAMB | Bedale Road | Between 67-83 Bedale Road, Aiskew | Aiskew | 27/07/2015 | 13/10/2015 |  | 02/12/2015 | N/A | 2 (1 SLIGHT- 1 SERIOUS) | 0 | 30 | 29/03/16-05/04/16 | 30/32 | 37/37 | 21/04/16 | TBC
HB1510031 | HAMB | Bedale Road | 1-4 Stanley Terrace | Aiskew, Bedale | 05/11/2015 | 06/11/2015 |  | 29/01/2016 Redeployment requested 06/05/16 | N/A | 4 slight 4 Serious | 0 | 30 |  |  |  |  | TBC
HB1510050 | HAMB | Through the village | Outside Rosedene, Hornby | Hornby | 03/08/2015 | 13/10/2015 | N/A | 21/01/2016 | N/A | 0 | 0 | 30 | 09/02/2016-16/02/2016 | 34/33 | 41/40 | 16/02/2016 | MATRIX | 04/03/2016
HB1510060 | HAMB | East Cowton | Passed Ashtead House, East Cowton | East Cowton | 05/08/2015 | 13/10/2015 | N/A | 30/09/2015 | N/A | 0 | 0 | 30 | 09/02/2016-16/02/2016 | 24/24 | 31/31 | 16/02/2016 | NFA | 04/03/2016
HB1510070 | HAMB | Main Road | Main Road, Barbeck close to St Giles Close, Thirsk | Thirsk | 16/07/2015 | 13/10/2015 |  | 21/01/2016 - Redeployment 11/02/2016 | N/A | 0 | 0 | 30 | 16/02/16-23/02/16 | 27/26 | 31/29 | 24/02/2016 | NFA | 04/04/2016
HB1510080 | HAMB | Ashlands Road | Bankhead road up to Bankhead/ Ashlands Close, Northallerton | Northallerton | 28/08/2015 | 13/10/2015 | N/A | 21/01/2016 | N/A | 1 slight | 0 | 30 | 09/02/16-16/02/2016 | 25/25 | 32/31 | 16/02/2016 | NFA | 04/03/2016
HB1510100 | HAMB | Hilton Road | Hilton Road-Western Stretch Seamer | Seamer | 26/09/2015 | 15/10/2015 | N/A | 26/01/2016 | N/A | 2 Slight | 0 | 30 | 24/02/16 - 03/03/16 | 28/30 | 32/35 | 08/03/2016 | NFA | 31/03/2016
HB1510110 | HAMB | West Moor Lane | Raskelf | Raskelf | 12/08/2015 | 15/10/2015 | N/A | 05/02/2016 | N/A | 0 | 0 | 30 | 10/04/2013 17/04/2013 | 34/32 | 39/38 | N/A | NFA | 12/02/2016
HB1510130 | HAMB | Danby Lane | Between Northallerton Rigg & Danby Wiske Village | Northallerton | 19/10/2015 | 05/11/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | 21/10/15 |  |  |  | 60-Back to Highways
HB1510160 | HAMB | Doctors Lane | Whole of Doctors Lane, Yarm | Hutton Rudby, Yarm | 02/11/2015 | 05/11/2015 | N/A | 09/12/2015 | N/A | 0 | 0 | 30 | 11/01/2016 - 19/01/2016 | 18/18 | 22/22 | 20/01/2016 | NFA | 12/02/2016
HB1510170 | HAMB | A6055 Gatenby roundabout | Gatenby roundabout to Leeming Bar roundabout | Romanby, Northallerton | 09/11/2015 | 10/11/2015 | N/A | N/A | 21/04/16 | 2 Slight 4 Serious | 0 | 60 |  |  |  |  | 60-Back to Highways
HB1510180 | HAMB | A684 Morton on Swale | From Bedale, Nr bus stop | Northallerton | 11/11/2015 | 12/11/2015 | TBC | 09/02/2016 | N/A | 6 Slight 1 Serious | 1 Slight | 30 | 22/02/16-29/02/16 re deployed 16/03/16-23/03/16 | 22/14 new-33/35 | 25/25 new -41/43 | 29/02/2016 re sent 21/04/16 | TBC
HB1510190 | HAMB | B6285 Theakston between Burniston and Exelby | At Theakston Hargill | Northallerton | 25/11/2015 | 26/11/2015 |  | N/A | 21/04/16 | 4 Slight and 1 Serious | 3 slight ( 2 on the s bend) | 60 |  |  |  |  | 60-Back to Highways
HB1510200 | HAMB | York Road | Vicinity of the Secondary School, Easingwold | Easingwold | 21/09/2015 | 15/10/2015 |  | 11/01/2016 - Redeployment 11/02/2016 | N/A | 1 Slight | 0 | 30 | 23/02/16- 01/03/16 | 28/30 | 31/34 | 02/03/2016 | NFA | 04/04/2016
HB1510210 | HAMB | Ainderby Road | Between Chantry Road and Lees Lane | Romanby | 04/12/2015 | 07/12/2015 | N/A | 09/02/2016 | N/A | 0 | 0 | 30 | 22/02/16 -29/02/16 | 30/29 | 35/34 | 29/02/2016 | NFA | 04/04/2016
HB1510230 | HAMB | Mill Hill Lane | Between Oak Mount Court and Colston Road/Millfield Lane | Northallerton | 12/01/2016 | 15/01/2016 | AWAITING SITE REVIEW | 09/02/2016 | N/A | 0 | 0 | 30 | 07/03/2016 - 14/03/2016 | 33/33 | 38/39 | 18/03/2016 | ENFORCEMENT | 04/04/2016
HB1520140 | HAMB | A167 Great Smeaton | Great Smeaton | Great Smeaton | 27/10/2015 | 05/11/2015 | N/A | 08/02/2016 | N/A | 2 slight 1 serious ( none of which are in the village 30's) | 0 | 30 | 09/02/16-16/02/16 | 30/31 | 34/35 | 16/02/2016 | NFA | 04/03/2016
HB1520150 | HAMB | Hornby Road | Hornby Road through Appleton Wiske | Appleton Wiske | 28/10/2015 | 05/11/2015 |  | 08/02/2016 | N/A | 0 | 0 | 30 | 29/02/16 - 07/03/16 | 24/24 | 32/31 | 08/03/2016 | TBC
HB1610120 | HAMB | Main Street | Approaching the village from York & Raskelf Road | Helperby | 16/02/2016 | 16/02/2016 | N/A | N/A | N/A | 0 | 0 | 30 | 13/01/2015 | 20/01/2015 | 31 | 26/03/16 | NFA
HB1610220 | HAMB | Long Lane | Hornby | Hornby | 01/03/2016 | 02/03/2016 | N/A | N/A | 21/04/16 | 0 | 0 | 60 |  |  |  |  | 60-Back to Highways
HB1610240 | HAMB | B1448 Norby Front Street | Norby Front Street between the Church and Mill Gardens estate | Norby, Thirsk | 30/01/2016 | 02/02/2016 | N/A | 02/05/2013 | N/A | 0 | 0 | 30 | 02/05/13 - 09/05/2013 | 35/32 | 41/38 | N/A | NFA
HB1610250 | HAMB | Thirsk Road | Near to 74 Thirsk Road | Northallerton | 05/02/2016 | 05/02/2016 | AWAITING SITE REVIEW | 24/02/2016 | N/A | 2 slight | 0 | 30 | 07/03/2016 - 14/03/2016 | 33/36 | 38/41 | 18/03/2016 | ENFORCEMENT | 04/04/2016
HB1610260 | HAMB | Stokesley Road | From Roundabout leaving Northallerton to Brompton junction | Northallerton | 17/02/2016 | 17/02/2016 |  | 08/03/2016 Redeployment requested 25/04/16 | N/A | 8 slight and 2 serious ( 1 serious speed related) to just past Mowbray road | 1 serious | 30 into the 40 |  |  |  |  | TBC
HB1610270 | HAMB | A167 Stainthorpe Row | A167 junction with Station Road, through South Otterington village | South Otterington | 02/03/2016 | 02/03/2016 |  | 16/03/2016 | N/A | 2 slight (not speed related) | 0 | 30 (60 into 30) | 28/04/16-05/05/16 | 28/31 | 36/38 | 06/05/2016 | TBC
HB1610280 | HAMB | Linton Woods Lane | The junction of Linton Woods lane, and Linton On Ouse Main Street which is the only road from Linton On Ouse Primary school | Linton on Ouse | 04/03/2016 | 08/03/2016 |  | 16/03/2016 | N/A | 0 | 0 | 40 | 21/04/2016 - 28/04/2016 | 21/20 | 25/24 | 28/04/2016 | TBC
HB1610290 | HAMB | Front Street, Sowerby | By 107A Front Street | Sowerby, Thirsk | 05/04/2016 | 07/04/2016 |  | N/A | N/A | 1 slight (not speed related) | 0 | 30 |  |  |  |  | NFA
HB1610300 | HAMB | Dalton Lane | Through the village | Nr Thirsk | 06/04/2016 | 07/04/2016 | N/A | N/A | N/A | 0 | 0 | 30 |  |  |  |  | NFA
HB1610310 | HAMB | Tame Bridge | Unnamed road from Stokesley to Hutton Rudby | Stokesley, Middlesbrough | 05/04/2016 | 11/04/2016 |  | 26/04/2016 | N/A | 1 slight (not speed related) | 0 | 40
HB1610320 | HAMB | A684 | Winton Bank | Northallerton | 09/04/2016 | 11/04/2016 |  | N/A | 21/04/16 | 1 slight | 1 slight | 60 |  |  |  |  | 60-Back to Highways
HB1610330 | HAMB | Meadow Lane | 86 Meadow Lane to the junction leaving Meadow Lane, Northallerton | Northallerton | 22/04/2016 | 22/04/2016 |  | 05/05/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
HB1610340 | HAMB | Skates Lane | Skates Lane into Bell Lane | Huby | 11/04/2016 | 22/04/2016 |  | 29/04/2016 | N/A | 1 serious | 0 | 30
HB1610350 | HAMB | Station Road and Sykes Lane | Through Tollerton Village | Helperby, York | 05/01/2016 | 08/01/2016 | N/A | 09/02/2016- Redployment requested 29/04/16 | N/A | 1 slight | 0 | 30 | 21/04/16-29/04/16 | 32/31 | 38/36 | 05/05/2016 | TBC
HB1610360 | HAMB | Busby Lane | Busby Lane into Kirkby Lane | Kirkby-In-Cleveland | 05/05/2016 | 06/05/2016 | . | 12/05/2016 | N/A | [7 empty] | TBC
HB1610370 | HAMB | Tanpit Lane | Full Length of Tanpit Lane, Easingwold | Easingwold | 05/05/2016 | 06/05/2016 | N/A | 12/05/2016 | N/A |  |  | 30 |  |  |  |  | TBC
HB1610380 | HAMB | Easby Lane | Bridge Street | Great Ayton | 08/05/2016 | 11/05/2016 | N/A | N/A | N/A |  |  |  | Recently investigated - October 2014 | 30/27 | 36/35 | N/A | NFA | N/A
HB1610390 | HAMB | Topcliffe Road | Sowerby, Thirsk | Sowerby, Thirsk | 10/05/2016 | 11/05/2016 | N/A | N/A | N/A |  |  | 30 | June 2014 | 23/24 | 28/28 | N/A | NFA | N/A
HG1410010 | HARROGATE | North & South of Ripley Village | Ripley | Harrogate | 18/11/2014 | 18/11/2014 |  | 14/01/2016 | N/A | 0 | 0 | 20
HG1410220 | HARROGATE | Norwich Drive | Harrogate | Harrogate | 18/12/2014 | 18/12/2014 | N/A | 20/10/2015 | N/A | 1 Slight | 0 | 20 | 01/12/2015 | 22/22 | 27/29 | 08/12/2015 | ENGINEERING | 26/04/2016
HG1410230 | HARROGATE | King Edwards Drive | Harrogate | Harrogate | 22/12/2014 | 22/12/2014 | . | 14/01/2016 | N/A | 0 | 0 | 30 | 28/01/16-04/02/16 | 21/22 | 27/27 | 05/02/2016 | TBC
HG1410280 | HARROGATE | Charlton Manor Drive | Knaresborough | Knaresborough | 22/05/2014 | 22/05/2014 |  | 08/12/2015 | N/A | 0 | 0 | 30 | 11/01/2016 - 18/01/2016 | 14/14 | 18/17 | 20/01/2016 | NFA | 27/04/2016
HG1510020 | HARROGATE | Leeming Lane | Kirby Hill | Kirby Hill | 04/03/2015 | 05/03/2015 |  | 14/01/2016 | N/A | 0 | 0 | 30 | 14/03/2016 - 21/03/2016 | 32/32 | 39/38 | 31/03/2016
HG1510030 | HARROGATE | Knaresborough Road | Bottom of Gallow Hill to the end at junction with Quarry Moor Road | Harrogate | 10/03/2015 | 11/03/2015 | N/A | 11/03/2015 | N/A | 0 | 0 | 30 | 20/10/2015 - 27/10/2015 | 28/27 | 33/31 | 20/11/2015 | NFA | 27/04/2016
HG1510040 | HARROGATE | Tockwith Village | Fleet lane, Westfield Lane, Marston Road direction of Long Marston | Tockwith | 23/03/2015 | 24/03/2015 | N/A | 24/03/2015 | N/A | 4- 2 Slight-2 Serious | 0 | 30 | 20/10/2015 - 27/10/2015 | 24/28 | 29/33 | 20/11/2015 | NFA | 27/04/2016
HG1510050 | HARROGATE | St Winifreds Avenue | Cars speeding and mounting the pavement | Harrogate | 30/03/2015 | 31/03/2015 | N/A | 29/01/2016 | N/A | 0 | 0 | 30 | 09/02/2016-16/02/2016 | 17/14 | 21/18 | 16/02/2016 | NFA | 27/04/2016
HG1510060 | HARROGATE | A61 | From A61 onto Smiths Lane (into village) | Hutton Conyers, Ripon | 27/02/2015 | 27/02/2015 | N/A | 27/02/2015 | N/A | 0 | 0 | 30 | 24/11/2015 - 01/12/2015 | 18/12 | 25/18 | 21/01/2016 | NFA | 27/04/2016
HG1510061 | HARROGATE | A61 Leeds Road | Leeds Road, Harrogate | Harrogate | 26/05/2015 | 27/05/2015 | AWAITING SITE REVIEW | 29/01/2016 | N/A | 16=13 Slight/ 3 Serious | 3 =2 Serious/ 1 Slight | 30 | 09/02/2016-16/02/2016 | 37/32 | 42/38 | 16/02/2016 | ENFORCEMENT | 27/04/2016
HG1510062 | HARROGATE | A61 | Opposite Landrover garage to Berrygate lane. | Ripon | 22/07/2015 | 22/07/2015 | . | 05/02/2016 | N/A | 3 Slight | 0 | 40 | 07/03/2016 - 14/03/2016 | 30/30 | 33/35 | 18/03/2016 | TBC
HG1510070 | HARROGATE | Leadhall Lane | Between junction of Leadhall Lane & Mallinson Way | Beckwithshaw | 08/04/2015 | 09/04/2015 |  | 26/01/2016 | N/A | 0 | 0 | 30 | 17/02/16-24/02/16 | 34/35 | 40/40 | 29/02/2016
HG1510080 | HARROGATE | Blazefield Bank to Windmill Cottage | Arton House off Blazefield bank, Pately Bridge | Pately Bridge | 13/04/2015 | 13/04/2015 | N/A | N/A | 21/04/16 | 2 -1 Slight-1 Serious | 1 Slight | 60 |  |  |  |  | 60-Back to Highways
HG1510090 | HARROGATE | Mallorie Park Drive | Mallorie Park Drive | Ripon | 01/05/2015 | 01/05/2015 | N/A | 01/06/2015 | N/A | 1 Slight | 0 | 30 |  | 29/29 | 34/33 | 29/01/2016 | NFA | 23/06/2015
HG1510100 | HARROGATE | Briggate | Briggate, Knaresborough | Knaresborough | 02/06/2015 | 02/06/2015 | N/A | 03/02/2016 | N/A | 1 Slight | 0 | 30 | 18/02/16-25/02/16 | 25/24 | 29/27 | 29/02/2016 | NFA | 27/04/2016
HG1510110 | HARROGATE | Law Lane | Law lane, Harrogate | Clint | 24/05/2015 | 24/05/2015 | N/A | N/A | N/A | 1 Slight | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510120 | HARROGATE | Boroughbridge Road | Balk Top to Dishforth Camp | Dishforth Airfield, Thirsk | 22/03/2015 | 23/03/2015 |  | 26/01/2016 | N/A | 0 | 0 | 30
HG1510130 | HARROGATE | Low Moor Lane | Scotton | Scotton | 11/06/2015 | 11/06/2015 | . | 03/02/2016 | N/A | 1 Slight | 0 | 30 | 14/03/2016 - 21/03/2016 | 23/25 | 29/31 | 31/03/2016 | TBC
HG1510140 | HARROGATE | Church Lane | Pannal | Pannal | 11/06/2015 | 11/06/2015 | N/A | 03/02/2016 | N/A | 0 | 0 | 30 | 17/02/16-24/02/16 | 29/28 | 32/32 | 29/02/2016 | NFA | 27/04/2016
HG1510150 | HARROGATE | Boroughbridge Road | Dishforth Airfield area, in 30mph zone near Boroughbridge Road/North Hill Road junction | Dishforth, Thirsk | 11/06/2015 | 11/06/2015 |  | 26/01/2016 | N/A | 3 Slight | 0 | 30
HG1510151 | HARROGATE | Boroughbridge Road | Boroughbridge Road onto Stockwell Drive | Knaresborough | 31/07/2015 | 31/07/2015 | . | 04/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
HG1510160 | HARROGATE | Yew Tree Lane | Using Yew Tree Lane as a shortcut to the A61 | Harrogate | 26/06/2015 | 26/06/2015 | N/A | 03/02/2016 | N/A | 1 Serious | 0 | 30 | 09/02/2016 - 16/02/2016 | 32/32 | 37/38 | 16/02/2016 | NFA | 27/04/2016
HG1510170 | HARROGATE | B6451 | Darley Mill Centre and Wellington Inn | Darley | 20/07/2015 | 20/07/2015 |  | 04/02/2016 | N/A | 0 | 0 | 40
HG1510180 | HARROGATE | Skelton Village | Skelton-on-Ure | Ripon | 20/07/2015 | 20/07/2015 | N/A | 20/07/2015 | N/A | 0 | 0 | 30 | 28/01/16 - 04/02/16 | 24/25 | 31/30 | 05/02/2016 | NFA | 27/04/2016
HG1510190 | HARROGATE | Harrogate Road | Bishop Monkton | Between Monkton Moor Garage (top of the hill Wormald Green) and Cascade Garden centre (Bishop Monkton crossroads) | 20/07/2015 | 22/07/2015 | N/A | N/A | 21/04/16 | 2 Serious 4 Slight | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510200 | HARROGATE | Bar Lane | Just past The Crown Inn Roecliffe | Roecliffe | 07/08/2015 | 07/08/2015 | . | 05/02/2016 | N/A | 2 Serious | 0 | 30 | 14/03/2016 - 21/03/2016 | 27/26 | 32/32 | 31/03/2016 | TBC
HG1510210 | HARROGATE | Shaw Lane | Beckwithshaw | Beckwithshaw | 10/06/2015 | 10/06/2015 |  | 03/02/2016 | N/A | 1 Serious 2 Slight | 1 Slight | 30
HG1510240 | HARROGATE | Main Street, Summerbridge | Summerbridge | Summerbridge | 22/01/2015 | 22/01/2015 | YES - LIVE SITE | 22/01/2015 | N/A | 0 | 0 | 30 | N/A | N/A | N/A | Note New Camera site already active here | TBC | 06/05/2016
HG1510250 | HARROGATE | Ripon Road | Harrogate | Harrogate | 09/02/2015 | 09/02/2015 | . | 29/01/2016 | N/A | 2 Slight | 1 Slight | 40 at junc of Grey hill Road into 30 just past junction |  |  |  |  | TBC
HG1510251 | HARROGATE | High Street | Low Wath Road | Pateley Bridge, Harrogate | 21/12/2015 | 21/12/2015 | . | 09/02/2016 | N/A | 0 Low Wath Road | 0 | 30 |  |  |  |  | TBC
HG1510260 | HARROGATE | Halfpenny Lane | Knaresborough | Knaresborough | 09/02/2015 | 09/02/2015 | N/A | 09/02/2015 | N/A | 2 Slight | 1 Slight | 30 |  |  |  |  | TBC
HG1510270 | HARROGATE | Electric Avenue | Harrogate | Harrogate | 19/05/2015 | 19/05/2015 | N/A | 08/12/2015 | N/A | 0 | 0 | 20 | 11/01/2016 - 18/01/2016 | 17/17 | 20/20 | 20/01/2016 | NFA | 26/04/2016
HG1510290 | HARROGATE | Nesfield Village | Common Holme Lane, Brant Bank Lane, W Hall Lane, Lowfield Lane, Beamsley Lane | Ilkley | 17/03/2015 | 17/03/2015 | N/A | N/A | 21/04/16 | 2 Slight | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510300 | HARROGATE | Main Street | Kirkby Malzeard | Harrogate | 09/02/2015 | 09/02/2015 |  | 09/02/2015 | N/A | 0 | 0 | 30 | 20/10/2015 - 27/10/2015 | 23/24 | 30/29 | 20/11/2015 | NFA | 26/04/2016
HG1510310 | HARROGATE | WoodLands Grove | Woodlands Grove, Harrogate | Harrogate | 13/10/2015 | 04/11/2015 | N/A | 08/02/2016 | N/A | 0 | 0 | 30 | 09/02/2016-16/02/2016 | 21/20 | 26/26 | 16/02/2016 | NFA | 27/04/2016
HG1510320 | HARROGATE | Rudding Lane | Rudding Lane, Harrogate | Follifoot, Harrogate | 19/10/2015 | 04/11/2015 | N/A | N/A | 21/04/16 | 1 Serious | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510330 | HARROGATE | Barrowby Lane | Barrowby Lane, Harrogate | Harrogate | 19/10/2015 | 04/11/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510380 | HARROGATE | Cornwall Road | Harlow Manor Road to Ebor Rise | Harrogate | 10/11/2015 | 10/11/2015 | . | 08/02/2016 | N/A | 1 Slight | 0 | 20 |  |  |  |  | TBC
HG1510400 | HARROGATE | Plumpton Park roundabout & Forest Lane | Between Plumpton Park roundabout and Forest Lane | Harrogate | 12/11/2015 | 17/11/2015 | . | 08/02/2016 | N/A | 4 Slight 1 Serious | 0 | 20 | 15/04/2016 - 22/04/2016 | 24/26 | 31/32 | 04/05/2016 | TBC
HG1510410 | HARROGATE | Prospect Road | Junction with Knaresborough Road | Harrogate | 14/11/2015 | 17/11/2015 | . | 08/02/2016. Redeployment requested 25/04/16 | N/A | 1 Slight | 1 | 30 |  |  |  |  | TBC
HG1510420 | HARROGATE | Buck Hill (known locally only) road is continuation of Smithson's Lane | Road passed Fewston Reservior Church | Whitcliffe Lane, Ripon | 18/11/2015 | 18/11/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510430 | HARROGATE | Elton Lane | Through Clapham Green to and from Belmont Grosvenor School | High Birstwith, Harrogate | 23/11/2015 |  | . | 16/12/2015 | N/A | 2 Serious ( not speed related) | 0 | 30 |  |  |  |  | TBC
HG1510440 | HARROGATE | Harlow Park Drive & Harlow Crescent | On the bend outside 9 Harlow Crescent | Harrogate | 23/11/2015 | 23/11/2015 | . | 09/02/2016. Redeployment request 25/04/16 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
HG1510450 | HARROGATE | Windsor Lane | From Gracious Street junction, along Windsor Lane, Stockdale Walk and Aspin Lane. | Knaresborough | 01/12/2015 | 01/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
HG1510470 | HARROGATE | Farnham Lane | From Eastwood to Grange View | Ferrensby | 07/12/2015 | 08/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 30 in the village otherwise 60. | 14/03/2016 - 21/03/2016 | 16/15 | 19/18 | 31/03/2016 | TBC
HG1510480 | HARROGATE | Castle Street | A661, Spofforth | Spofforth | 09/12/2015 | 09/12/2015 | . | 08/02/2016 | N/A | 0 | 0 | 30 |  | 35/33 | 41/38 | 16/12/2015 | TBC
HG1510490 | HARROGATE | Southgate | Full length of Southgate, Ripon | Ripon | 10/12/2015 | 11/12/2015 | . | 09/02/2016 | N/A | 1 Slight ( not speed related) | 0 | 30 | 07/03/2016 - 14/03/2016 | 20/19 | 25/23 | 18/03/2016 | TBC
HG1510500 | HARROGATE | Darley Carr | Darley | Darley | 20/07/2015 | 20/07/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 |  |  |  |  | 60-Back to Highways
HG1510520 | HARROGATE | Road past Clifton House | Summerbridge | Summerbridge | 22/01/2015 | 22/01/2015 | YES - LIVE SITE | 03/02/2016 | N/A | 2 slight 1 serious on East View (not speed related) | 0 | 30 | N/A | N/A | N/A | N/A | TBC | 06/05/2016
HG1530340 | HARROGATE | B6163 Thistle Hill | Thistle Hill, Harrogate | Harrogate | 02/11/2015 | 04/11/2015 | . | 08/02/2016 | N/A | 0 | 0 | 40 |  |  |  |  | TBC
HG1530350 | HARROGATE | Forest Moor Road | Forest Moor Road, Knaresborough | Knaresborough | 02/11/2015 | 05/11/2015 |  | 08/02/2016 | N/A | 3 Slight 1 Fatal | 0 | 40 | 14/03/2016 - 21/03/2016 | 37/38 | 41/43 | 31/03/2016
HG1530370 | HARROGATE | Skipton Road | All the way down Skipton Road but particularly Skipton Road and Kings Road Junction | Harrogate | 09/11/2015 | 10/11/2015 | . | 08/02/2016 | N/A | 11 Slight/5 Serious from Railway line to Majestic Wines | 2 Slight from Railway line to Majestic Wines | 30 |  |  |  |  | TBC
HG1530390 | HARROGATE | Castle Street | 1 High Street onwards 1 Castle Street onwards Follifoot Lane - A59 | Spofforth | 10/11/2015 | 10/11/2015 | . | 08/02/2016 | N/A | 0 | 0 | 30 | 26/04/2016 - 03/05/2016 | 29/29 | 34/34 | 04/05/2016 | TBC
HG1530460 | HARROGATE | Otley Road | Full length including in front of Primary School | Killinghall | 03/12/2015 | 07/12/2015 | N/A | 08/12/2015 | N/A | 5 Slight | 1 Slight-Junc of Grainbeck Lane | 30 | 11/01/2016 - 18/01/2016 | 32/30 | 36/35 | 20/01/2016 | NFA | 29/01/2016
HG1540340 | HARROGATE | B6163 Thistle Hill | Through Calcutt, Blands Hill, Belmont Grove to the junction with Forest Moor Road then up Thitsle Hill | Calcutt | 06/11/2015 | 10/11/2015 | . | 08/02/2016 | N/A | 1 Slight | 1 | 30 |  |  |  |  | TBC
HG1610530 | HARROGATE | A658 Harrogate Road | The stretch of the road at the Farm shop and Hunters Inn, past the Petrol station to beyond the Riffa Business Park | Harrogate | 20/01/2016 | 25/01/2016 | N/A | N/A | 21/04/16 | 2 Serious 4 slight | 1 Slight | 60 |  |  |  |  | 60-Back to Highways
HG1610540 | HARROGATE | Quarry Moor Lane | Near Greystone C P School | Ripon | 21/01/2016 | 25/01/2016 | N/A | 09/02/2016 | N/A | 1 Slight (not speed related) | 0 | 20 | 07/03/16-14/03/16 | 25/22 | 30/27 | 15/03/2016 | MATRIX | 27/04/2016
HG1610550 | HARROGATE | Main Street | Near the School, Knaresbrough | Staveley, Knaresbrough | 25/01/2016 | 26/01/2016 | . | 09/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
HG1610560 | HARROGATE | Cold Bath Road | Junction of Westcliffe Road | Harrogate | 28/01/2016 | 02/02/2016 | . | 09/02/2016 | N/A | 4 slight (not speed related) | 0 | 20 |  |  |  |  | TBC
HG1610570 | HARROGATE | A661 | Near to East Field Farm, Massey Fold | Spofforth, Harrogate | 30/01/2016 | 02/02/2016 | . | 24/02/2016 | N/A | 1 slight | 0 | 30 | 03/05/2016 - 09/05/2016 | 25/27 | 29/31 | 11/05/2016 | TBC
HG1610580 | HARROGATE | Dishforth Road | Glebe Meadow though the village | Ripon | 09/02/2016 | 09/02/2016 | . | 02/03/2016 | N/A | 0 | 0 | 30 | 04/05/16-10/05/16 | 31/30 | 37/35 | 12/05/2016 | TBC
HG1610590 | HARROGATE | Market Flat Lane | Near The Old Kennels in the 60mph | Scotton, Knaresborough | 10/02/2016 | 11/02/2016 | . | 12/04/16 | 21/04/16 | 2 slight (not speed related) | 0 | 40 | 04/05/16-11/05/16 | 37/39 | 45/46 | 12/05/2016 | TBC
HG1610600 | HARROGATE | Burn Bridge Road | Burn Bridge, Harrogate | Burn Bridge | 12/02/2016 | 12/02/2016 | . | 08/03/2016 | N/A | 1 from Black Swan Inn to Hillfoot Lane junc ( this is not speed related and is at the junction of hillfoot lane) | 0 | 30 | 26/04/2016 - 03/05/2016 | 28/25 | 32/29 | 04/05/2016 | TBC
HG1610610 | HARROGATE | Abbey Road | Waterside crossing to Abbey Road, Knaresborough | Knaresborough | 12/02/2016 | 16/02/2016 | . | 08/03/2016 | N/A | 1 slight | 1 slight | 30 |  |  |  |  | TBC
HG1610620 | HARROGATE | A61 Baldersby | Past Blue Row/Smithy's Farm Shop | Baldersby | 06/12/2015 | 07/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 30 | 07/04/16-12/04/16 | 24/24 | 27/27 | 21/04/16 | TBC
HG1610630 | HARROGATE | Church Lane, Hampsthwaite | Between Hampsthwaite Bridge and Hampsthwaite School | Hampsthwaite, Harrogate | 02/03/2016 | 02/03/2016 | . | 16/03/2016 | N/A | 1 slight just past the school-(not speed related) | 0 | 20 |  |  |  |  | TBC
HG1610640 | HARROGATE | Main Street, Pannal | On Main St, from Pannal Station, past Pannal Junior school up to 30mph sign on Church lane | Harrogate | 15/03/2016 | 16/03/2016 | N/A | Recently Investigated October 2013 | N/A | 0 | 0 | 30 | N/A | N/A | N/A | N/A | NFA | N/A
HG1610660 | HARROGATE | Leeds Road, Harrogate | Between St Mark's roundabout and Prince of Wales roundabout | Harrogate | 28/03/2016 | 04/04/2016 | N/A | Recently investigated Nov 2013 | N/A | 1 slight (not speed related) | 0 | 30 | N/A | N/A | N/A | N/A | NFA | N/A
HG1610670 | HARROGATE | Farnley Lane | Both directions of Farnley Lane (linking North Yorkshire & Leeds) | Burley in Wharfdale, Ilkley | 05/04/2016 | 07/04/2016 | . | 26/04/2016 | N/A | 1 serious (not speed related) | 0 | 40 |  |  |  |  | TBC
HG1610680 | HARROGATE | Whitcliffe Lane | Junction with Whitcliffe Crescent/Grove | Ripon | 03/05/2016 | 03/05/2016 | . | 12/05/2016 | N/A | 1 Serious (much further down Whitcliffe road) | 0 | [5 empty] | TBC
HG1610690 | HARROGATE | Tower Street | Near PureGym | Harrogate | 09/05/2016 | 11/05/2016 | N/A |  | N/A | [7 empty] | TBC
HG1610700 | HARROGATE | Drury Lane | Junction with Drury Close | Pannal | 10/05/2016 | 11/05/2016 | N/A | N/A | N/A |  |  |  | November 2014 | 56/54 | 64/63 | N/A | NFA | N/A
HG1610710 | HARROGATE | Hartwith Bank | Near Hartwith Green | Summerbridge | 10/05/2016 | 11/05/2016 | N/A |  | N/A |  |  | 30 |  |  |  |  | TBC
N/AHG1530360 | HARROGATE | Askwith Moor Road | near to: Snowden Bank Cottage, at the foot of Snowden Bank, near the junction with Snowden Carr Road. | Otley | 29/10/2015 | 05/11/2015 | . | 08/02/2016 | N/A | 1 Serious | 0 | 30 |  |  |  |  | TBC
N/AHG1610650 | HARROGATE | Hookstone Chase | Junction of Hookstone Close | Harrogate | 24/03/2016 | 24/03/2016 | N/A | Recently Investigated Nov 2014 | N/A | 4 slight/1 serious from the roundabout on Hookstone Chase to the Junctions of Woodlands | 1 slight | 30 | N/A | N/A | N/A | N/A | NFA
RM1510010 | RICH | Richmond Road | Brompton on Swale | Brompton on Swale | 09/07/2015 | 15/10/2015 | N/A | 30/09/2015 | N/A | 1 Serious 1 Slight | 1 slight | 30 | 17/11/2015-24/11/2015 | 26/23 | 32/33 | 25/01/2016 | NFA | 12/02/2016
RM1510011 | RICH | Richmond Road | Down the hill towards the junction at A167. 3 South Terrace and The Terrace | Croft on Tees | 20/11/2015 | 20/11/2015 | AWAITING SITE REVIEW | 08/01/2016 | N/A | 0 | 0 | 30 | 19/01/16-26/01/2016 | 36/36 | 43/43 | 26/01/2016 | ENFORCEMENT | 12/02/2016
RM1510020 | RICH | Station Road | All of Station Road, Brompton on Swale | Brompton on Swale | 09/07/2015 | 15/10/2015 | N/A | 30/09/2015 | N/A | 0 | 0 | 30 | 17/11/2015 to 24/11/2015 | 26/26 | 32 | 08/12/2015 | NFA | 12/02/2016
RM1510030 | RICH | Leyburn Road | Askrigg | Askrigg | 24/09/2015 | 15/10/2015 | N/A | 30/09/2015 | N/A | 1 Slight | 1 Slight | 30 | 30/10/2015 - 06/11/2015 | 26/24 | 31/29 | 20/11/2015 | NFA | 11/01/2016
RM1510040 | RICH | Aldbrough Road | Melsonby | Melsonby | 02/09/2015 | 15/10/2015 | . | 15/11/2015 | N/A | 0 | 0 | 30 | 09/11/15 -17/11/15 | 30/29 | 36/35 | 24/02/2016 | TBC
RM1510050 | RICH | West Road | Melsonby | Melsonby | 02/09/2015 | 15/10/2015 | N/A | 30/09/2015 | N/A | 0 | 0 | 30 | 09/11/2015 - 17/11/2015 | 25/22 | 30/29 | 16/12/2015 | NFA
RM1510060 | RICH | Gilling West High Street | Gilling West | Gilling West | 01/09/2015 | 15/10/2015 | N/A | 30/09/2015 | N/A | 4 Slight | 0 | 30 | 30/10/2015 - 06/11/2015 | 27/27 | 32/32 | 20/11/2015 | NFA | 11/01/2016
RM1510070 | RICH | Pallett Hill | Catterick Viliage | Catterick Village | 30/09/2015 | 15/10/2015 | N/A | 16/12/2015 | N/A | 1 Slight | 1 | 30 | 06/01/2016 - 14/01/2016 | 12/12 | 17/16 | 15/01/2016 | NFA | 29/02/2016
RM1510080 | RICH | West Witton | Both ends of the Village | West Witton | 08/10/2015 | 15/10/2015 | AWAITING SITE REVIEW | 11/01/2016 | N/A | 1 Serious | 0 | 30 | 26/01/2016-02/02/2016 | 29/29 (west end) 34/36 (east end) | 33/33 (west end) 40/42 (east end) | 04/02/2016 | ENFORCEMENT | 04/03/2016
RM1510090 | RICH | Queen's Road | Queen's Road into Dundas Street | Richmond | 26/10/2015 | 04/11/2015 | N/A | 16/12/2015 | N/A | 0 | 0 | 20 | 06/01/2016 - 14/01/2016 | 22/20 | 26/24 | 15/01/2016 | ENGINEERING
RM1510100 | RICH | B6275 Barton to Piercebridge | Barton to Piercebridge | Aldbrough St John | 03/11/2015 | 05/11/2015 | N/A | N/A | 21/04/16 | 3 Slight 3 Serious | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
RM1510110 | RICH | Haig Road | Whole of Haig Road, Catterick Garrison | Catterick Garrison | 09/11/2015 | 10/11/2015 | N/A | 02/12/2015 | N/A | 0 | 0 | 30 | 02/02/2016 - 09/02/16 | 27/28 | 33/33 | 09/02/2016 | NFA | 04/03/2016
RM1510120 | RICH | Un-named Road known as Cookson Way | From roundabout on A6136 to Gilesgate Roundabout.The road is the entry road to Gilesgate and situated off the roundabout next to the NISA Filling Station A6136 on Catterick Road (Postcode for garage DL9 4RZ) | Catterick Garrison | 23/11/2015 | 23/11/2015 | N/A | 11/01/2016 | N/A | 0 | 0 | 30 | 14/01/2016-21/01/2016 | 24/22 | 29/27 | 25/01/2016 | NFA | 12/02/2016
RM1510130 | RICH | Brokes | Through Brokes farms, Richmond | Brokes, Richmond | 01/12/2015 | 02/12/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
RM1510140 | RICH | A684 Constable Burton Village | Between Bedale and Leyburn | Constable Burton | 01/12/2015 | 07/12/2015 | N/A | 05/02/2016 | N/A | 2 slight (one either end of village) | 1 prior to village Bedale end | 40 | 18/06/2013 | 40 | 45 | N/A | NFA | 08/02/2016
RM1530150 | RICH | B6274 Caldwell Village | Passed Brownlow Arms leading towards Eppleby | High Row, Caldwell, Richmond | 07/12/2015 | 07/12/2015 | N/A | N/A | N/A | 1 Serious (not speed related) | 0 | 30 | 13/09/13 | 25/27 | 33/33 | N/A | NFA | 25/02/2016
RM1610160 | RICH | West End, Tunstall Village | Top end of village (West End) | Tunstall, Richmond | 22/03/2016 | 24/03/2016 | . | 21/04/2016 | N/A | 1 slight | 1 slight | [5 empty] | TBC
RM1610170 | RICH | A684 Harmby to Leyburn | Harmby to Leyburn | Leyburn | 23/03/2016 | 04/04/2016 | . | 21/04/2016 | N/A | 3 serious 1 slight (not speed related) | 0 | 40 |  |  |  |  | TBC
RM1610180 | RICH | Green Howards Road | Full length of Green Howards Road, Richmond | Richmond | 06/04/2016 | 07/04/2016 | . | 21/04/2016 | N/A | 1 slight (not speed related) | 0 | [5 empty] | TBC
RM1610190 | RICH | Gilling Road, Richmond | Outside no 50 | Richmond | 06/04/2016 | 07/04/2016 | . | 21/04/2016 | N/A | 0 | 0 | [5 empty] | TBC
RM1610200 | RICH | Hudswell Lane | Whole village of Hudswell, Richmond | Richmond | 08/04/2016 | 11/04/2016 | N/A | 26/04/2016 | N/A | 2 serious (not speed related)either side of the Hollies Farm entrance (Holly Hill end) | 0 | 30 | N/A | N/A | N/A | N/A | NFA
RM1610210 | RICH | Slee Gill | Richmond | 16, Slee Gill | 03/05/2016 | 03/05/2016 | . | N/A | N/A | 1 slight by the Outdoor Centre | 0 | 30 |  |  |  |  | TBC
RM1610220 | RICH | Dundas Street | Richmond | Richmond | 10/05/2016 | 11/05/2016 | N/A |  | N/A | [7 empty] | TBC
RY1510010 | RYE | Beverley Road | Norton | Malton | 08/06/15 | 08/06/15 | N/A | 08/07/2015 | N/A | 3 Slight | 0 | 30 | 21/01/2016 - 01/02/2016 | 31/31 | 37/37 | 11/02/2016 | NFA | 26/04/2016
RY1510020 | RYE | Princess Road | Malton | Malton | 18/08/15 | 26/08/15 | N/A | 07/12/2015 | N/A | 3 Slight | 1 Slight | 30 | 21/01/206 - 30/01/2016 | 26/27 | 31/32 | 11/02/2016 | NFA | 26/04/2016
RY1510030 | RYE | A170 | Middleton/Aislaby | Pickering | 25/08/2015 | 26/08/2015 | N/A | 16/01/2016 | N/A | 2 Slight 1 Serious | 0 | 30 |  |  |  |  | TBC
RY1510040 | RYE | Langton Road | Near St. Peters Crescent | Malton | 02/10/15 | 02/10/15 | N/A | 08/12/2015 | N/A | 0 | 0 | 30 | 06/01/2016 - 15/01/2016 | 28/29 | 34/34 | 20/01/2016 | NFA | 04/03/2016
RY1510050 | RYE | Middleton Road | Opposite North Road | Pickering | 25/11/2015 | 25/11/2015 | AWAITING SITE REVIEW | 09/02/2016 | N/A | 0 | 0 | 30 | 23/03/16-30/03/16 | 30/28 | 38 | 19/04/16 | ENFORCEMENT | 26/04/2016
RY1510060 | RYE | Rice Lane | Flaxton | Flaxton | 30/10/2015 | 05/11/2015 | N/A | 16/12/2015 | N/A | 0 | 0 | 40 | No post suitable for logger | N/A | N/A | N/A | NFA | 25/04/2016
RY1510070 | RYE | A170 | East from Kirkbymoorside towards Pickering first junction to Sinnington | Sinngington, York | 10/12/2015 | 11/12/2015 | N/A | N/A | 21/04/16 | 3 serious 1 fatal ( from dawsons wood to just past junc of Sinnington) | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
RY1610080 | RYE | Malton Road | Marton near Kirkbymoorside connecting to A170 | Sinnington, York | 19/01/2016 | 20/01/2016 | . | 16/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610090 | RYE | Main Street | Full length of Main Street, Flaxton | Flaxton | 27/01/2016 | 29/01/2016 | . | 16/02/2016 | N/A | 0 | 0 | 30 | 18/03/16-24/03/16 | 33/33 | 39/40 | 25/04/16 | TBC
RY1610100 | RYE | Horsemarket Road | Malton | Malton | 03/02/2016 | 05/02/2016 | N/A | N/A | N/A | 2 slight ( 1 speed related) | 1 | 30 | N/A | N/A | N/A | N/A | NFA | 12/02/2016
RY1610110 | RYE | Peasey Hills Road | Near Gilling Way /Burke Road | Malton | 13/02/2016 | 16/02/2016 | . | 15/03/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610120 | RYE | Low Moorgate | Rillington | Rillington | 16/02/2016 | 17/02/2016 | N/A | N/A | N/A | 1 slight ( not speed related) and in the 30's | 0 | 30 into 60 | N/A | N/A | N/A | N/A | NFA | 23/02/2016
RY1610130 | RYE | York Road | York Road exiting and entering 30mph sign to traffic lights in Malton | Malton | 24/02/2016 | 26/02/2016 | N/A | 16/03/2016 | N/A | 4 slight 1 serious | 1 slight | 30 |  |  |  |  | TBC
RY1610131 | RYE | York Road | Leavening Whin Hill | Leavening, Malton | 16/04/2016 | 18/04/2016 | . | 29/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610140 | RYE | West End Ampleforth | Near White Horse Inn | Ampleforth | 25/02/2016 | 26/02/2016 | . | 16/03/2016 | N/A | 0 | 0 | 30 | 08/04/16-13/04/16 | 26/26 | 35/34 | 21/04/16 | TBC
RY1610150 | RYE | Westgate Carr Road | Between 'Rosti' and the junction to Westgate | Pickering | 29/02/2016 | 01/03/2016 | . | 16/03/2016 | N/A | 0 | 0 | 30 | 30/03/16-07/04/16 | 29/29 | 36/35 | 21/04/16 | TBC
RY1610160 | RYE | Eastgate - Thornton Road | From Hawthorn Lane | Pickering | 03/03/2016 | 04/03/2016 | . | 16/03/2016 | N/A | 4 slight (1 speed related) | 1 slight | 30 | 06/04/16-18/04/16 | 30/32 | 34/38 | 25/04/16 | TBC
RY1610170 | RYE | Church Hill/High Street | Near New Hall Old People Residents Home | Thornton Le Dale | 04/03/2015 | 04/03/2015 | N/A | N/A | N/A | 0 | 0 | 30 | 04/2015 | 27/31 | 32/37 | N/A | NFA | 11/03/2016 - Recently investigated
RY1610180 | RYE | Main Street into Dam Lane | Gannow Junction with Dam Lane | Leavening, Malton | 15/03/2016 | 15/03/2016 | N/A | 07/04/2016 | N/A | 0 | 0 | N/A | N/A | N/A | N/A | N/A | NFA
RY1610190 | RYE | Yatts Road | Outside Rosecroft, Yatts Road | Newton on Rawcliffe, Pickering | 28/03/2016 | 04/04/2016 | . | 24/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610200 | RYE | Barugh Lane | Prospect House, Howardian View, on the bend and all the way up the hill towards the Golden Lion pub. | Malton | 02/04/2016 | 04/04/2016 | . | 26/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610210 | RYE | Main Street, Welburn | Near Tamarisk Cottage | Welburn | 04/04/2016 | 07/04/2016 | . | 26/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
RY1610220 | RYE | B1257 at Stonegrave | Carr Lane (Cawton Road known locally) | Stonegrave | 03/05/2016 | 03/05/2016 | . | 12/05/2016 | N/A | 0 | 0 | 40 |  |  |  |  | TBC
SC1510010 | SCAR | Main Street | Cayton | Whitby | 26/06/2015 |  | N/A | 26/08/2015 | N/A | 1 Serious 2 Slight | 0 | 30 | 10/11/2015 - 19/11/2015 | 30/28 | 35/33 | 21/01/2016 | NFA | 29/01/2016
SC1510020 | SCAR | Racecourse Road | East Ayton | East Ayton, Scarborough | 26/08/2015 |  | AWAITING SITE REVIEW | Redeployment 27/01/2016 & Redeployment 24/02/16 -multi data | N/A | 7 Slight 1 Serious | 1 Slight | 30 into 60 | 07/03/2016 - 14/03/2016 | 36/35 | 41/40 | 15/03/2016 | ENFORCEMENT | 26/04/2016
SC1510030 | SCAR | Castle Road | Whitby | . | 20/09/2015 |  | . | Redeployed 27/01/2016 | N/A | 1 serious 1 Slight | 0 | 30 | 31/03/16-07/04/16 | 33/34 | 38/39 | 21/04/16 | TBC
SC1510040 | SCAR | A174 | Through Lythe Village form Hinderwell. | Whitby | 17/11/2015 | 17/11/2015 | . | 24/12/2015 | N/A | 1 Slight- not speed related | 0 | 30 in village | 19/04/2016 - 28/04/2019 | 31/34 | 37/40 | 04/05/2016 | TBC
SC1510050 | SCAR | B1410 Sleights to Ruswarp Road | Length of Briggswath | Briggswath, Whitby | 20/11/2015 | 20/11/2015 | N/A | 11/01/2016 | N/A | 1 Serious/1 Fatal | 0 | 30 | 15/20/16- 22/02/16 | 25/24 | 30/29 | 23/02/2016 | NFA | 26/04/2016
SC1510060 | SCAR | The Lane, Mickleby | Junction on West Lane, Low Lane, The Lane | Egton, Whitby | 21/11/2015 | 23/11/2015 | . | 02/12/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SC1510070 | SCAR | Stepney Road | Between Scarborough Sixth Form college and Jacoubs Mount Caravan Park | Scarborough | 27/11/2015 | 01/12/2015 | . | 05/02/2016 | N/A | 3 Slight 1 Serious | 1 Slight ( roundabout outside college) | 30 |  |  |  |  | TBC
SC1510080 | SCAR | Egton Road | Egton Road in the direction of Aislaby | Egton, Whitby | 27/11/2015 | 01/12/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | N/A | N/A | NA | N/A | 60-Back to Highways
SC1510090 | SCAR | High Sreet | Mainly 22-24 High Street, Ruswarp | Ruswarp | 27/11/2015 | 01/12/2015 | N/A | 16/12/2015 | N/A | 1 Slight | 0 | 20 | 15/02/16- 22/02/2016 | 25/24 | 30/29 | 23/02/2016 | ENGINEERING | 26/04/2016
SC1510100 | SCAR | A171 Stainsacre Lane | Near Sainsburys and Chomley Way | Whitby | 04/12/2015 | 07/12/2015 | AWAITING SITE REVIEW | 09/02/2016 | N/A | 0 | 0 | 30 | 15/02/16- 22/02/2016 | 34/33 | 39/38 | 23/02/2016 | ENFORCEMENT | 04/03/2016
SC1510110 | SCAR | Aislaby Lane | Whitby end of the village | Aislaby, Whitby | 18/12/2015 | 22/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 30 in village 60 out of village |  |  |  |  | TBC
SC1610120 | SCAR | Station Road | Main Street junction to railway crossing | Cayton, Scarborough | 06/01/2016 | 11/01/2016 | . | 09/02/2016 | N/A | 1 slight | 0 | 30 |  |  |  |  | TBC
SC1610130 | SCAR | Lingholme Lane | Lebberston | Cayton, Scarborough | 21/01/2016 | 21/01/2016 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
SC1610140 | SCAR | Wreyfield Drive | Full length of Wreyfield Drive | Newby, Scarborough | 27/01/2016 | 29/01/2016 | N/A | 09/02/2016 | N/A | 1 slight (not speed related) | 0 | 20 | 14/03/2016 - 22/03/2016 | 20/19 | 25/24 | 31/03/2016 | NFA | 26/04/2016
SC1610150 | SCAR | Dale Lane | Junction with Middle Lane leading into the village | Hutton Buscel, Scarborough | 06/02/2016 | 09/02/2016 | . | 08/03/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SC1610160 | SCAR | North Leas Avenue | By 55 North Leas Avenue, Scarborough | Scarborough | 28/03/2016 | 04/04/2016 | . | 25/04/2016 | N/A | 1 Serious | 0 | 20 |  |  |  |  | TBC
SC1610170 | SCAR | Northstead Manor Drive | Near no's 10 & 11 | Cayton | 01/04/2016 | 18/04/2016 | . | 26/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SC1610180 | SCAR | Newlands Avenue | Near Cleveland Avenue/Burniston Road | Discovery Way, Whitby | 21/04/2016 | 21/04/2016 | . | 05/05/2016 | N/A | 0 | 0 | [5 empty] | TBC
SC1610190 | SCAR | Woodlands Ravine | Near no. 16 | Discovery Way, Whitby | 21/04/2016 | 21/04/2016 | . | 05/05/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1310390 | SELBY | Mill Lane | Camblesforth | Camblesforth | 18/09/2013 | 03/10/2013 |  | 21/01/2016 | N/A | 1 slight (junc of mill lane and A1041) not speed related | 0 | 30 | 04/05/16-11/05/16 | 16/16 | 20/20 | 12/05/2016 | TBC
SE1310400 | SELBY | Manor Drive | Camblesforth | Camblesforth | 19/03/2013 | 03/10/2013 |  | 21/01/2016 | N/A | 0 | 0 | 30 | 04/05/16-11/05/16 | 15/15 | 19/20 | 12/05/2016 | TBC
SE1410250 | SELBY | Selby Road | Selby Road, Camblesforth | Camblesforth | 13/06/2015 | 13/06/2015 | N/A | 03/02/2016 | N/A | 4 slight ( 1 not speed related) | 3 slight | 40 | 10/02/16-17/02/2016 | 42/40 | 47/44 | 23/02/2016 | ENGINEERING | 25/04/2016
SE1410260 | SELBY | Cotchers Lane | Saxton, Tadcaster | Saxton, Tadcaster | 07/07/2014 | 10/08/2014 | . | 21/01/2016 | N/A | 0 | 0 | 30 | 15/03/2016 - 22/03/2016 | 18/19 | 23/25 | 31/03/2016 | TBC
SE1410280 | SELBY | Main Road | Hambleton | Hambleton | 25/11/2014 | 27/05/2014 | . | 03/02/2016 | N/A | 3 slight (2 not speed related) | 1 | 30 | 30/03/16-06/04/16 | 35/39 | 41/44 | 21/04/16 | TBC
SE1410380 | SELBY | York Road | Tadcaster | Tadcaster | 04/02/2014 | 10/02/2014 | . | 2015 | N/A | 2 slight (not speed related) | 0 | 30 |  |  |  |  | TBC
SE1410410 | SELBY | Weedling Gate | Stutton, Tadcaster | Stutton, Tadcaster | 16/01/2014 | 17/01/2014 | . | Redeployed 27/01/2016 | N/A | 0 | 0 | 30 | 15/03/2016 - 22/03/2016 | 22/23 | 27/27 | 31/03/2016 | TBC
SE1510010 | SELBY | Parkways | Selby | Selby | 02/06/2014 | 05/06/2014 | . | 16/12/2015 | N/A | 0 | 0 | 30 | 07/01/2016 - 14/01/2016 | 17/17 | 19/20 | 15/01/2016 | TBC
SE1510013 | SELBY | Sandway Avenue | Thorpe Willoughby | Thorpe Willoughby | 21/08/2015 | 21/08/2015 | . | 08/02/2016 | N/A | 0 | 0 | 30 | 22/02/2016 - 29/02/2016 | 15/15 | 19/19 | 01/03/2016 | TBC
SE1510020 | SELBY | High Street | Carlton | Goole | 13/05/2014 | 20/05/2014 | . | 21/01/2016 | N/A | 0 | 0 | 30 | Redeployment requested 31/03/2016 |  |  |  | TBC
SE1510030 | SELBY | Hirst Road | Chapel Heddlesey | Selby | 16/06/2015 | 03/07/2015 | N/A | 03/02/2016 | N/A | 1 Serious 3 Slight | 1 Slight | 30 | 08/03/2016 - 15/03/2016 and 15/03/2016 - 22/03/2016 | 28/27 and 29/26 | 35/34 and 36/32 | 31/03/2016 | NFA | 25/04/2016
SE1510040 | SELBY | Denison Road | Selby | Selby | 31/10/2014 | 10/11/2014 | N/A | 03/02/2016 | N/A | 2 Slight | 2 Slight | 30 | 10/02/16-17/02/16 | 25/24 | 31/30 | 23/02/2016 | NFA | 25/04/2016
SE1510050 | SELBY | Long Lane | Great Heck | Great Heck | 14/02/2015 | 14/02/2015 | N/A | 08/12/2015 | N/A | 1 Slight | 0 | 30 | 07/01/2016-14/01/2016 | 33/28 | 40/41 | 25/01/2016 | ENGINEERING | 25/04/2016
SE1510060 | SELBY | Wetherby Road | Outside Tadcaster Riverside School | Tadcaster | 25/11/2015 | 26/11/2015 | . | 11/01/2016 | N/A | 0 | 0 | 20 | 25/01/2016 - 01/02/2016 | 20/19 | 25/22 | 02/02/2016 | TBC
SE1510070 | SELBY | Main Street | Kellington | Kellington | 16/07/2015 | 16/07/2015 | . | 03/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1510080 | SELBY | Westbourne Road | Selby | Selby | 24/06/2015 | 02/07/2015 | N/A | 03/02/2016 | N/A | 2 Slight | 0 | 30 | 01/03/2016 - 08/03/2016 | 12/13 | 15/17 | 11/03/2106 | NFA | 25/04/2016
SE1510090 | SELBY | A162 Main Street | Towton | Main Street, Towton | 30/06/2015 | 03/07/2015 | . | 03/07/2015 | N/A | 0 | 0 | 30 |  | 31/32 | 36/37 | 01/12/2015 | TBC
SE1510100 | SELBY | Sutton Lane | Sutton, Tadcaster | Sutton, Nr Brotherton | 19/06/2015 | 02/07/2015 | . | 15/12/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1510120 | SELBY | Leeds Road | Toulston, Tadcaster | Toulston, Tadcaster | 20/08/2015 | 20/08/2015 | . | 20/08/2015 | N/A | 1 Slight | 1 Slight | 40 | 03/11/2015 - 10/11/2015 | 42/40 | 49/46 | 20/11/2015 | TBC
SE1510140 | SELBY | Field Lane | Thorpe Willoughby | Thorpe Willoughby | 21/08/2015 |  | . | 08/02/2016 | N/A | 0 | 0 | 30 | Redployment request 02/03/16 Dates? |  |  |  | TBC
SE1510150 | SELBY | New Road | Ulleskelf | Ulleskelf | 17/09/2015 | 21/09/2015 | . | 21/09/2015 | N/A | 0 | 0 | 30 | 03/11/2015 - 10/11/2015 | 28/28 | 34/33 | 20/11/2015 | TBC
SE1510170 | SELBY | A63 Hull Road | Hemingbrough - the long straight past park and R&R Country | Not Given | 13/10/2015 | 05/11/2015 | . | 16/12/2015 | N/A | 0 | 0 | 40 |  |  |  |  | TBC
SE1510180 | SELBY | Moor Lane & Pasture Way | Moor Lane Sherburn in Elmet travelling east from traffic lights in the Village Centre from speed bumps to mini roundabout near Pasture Way | Eversley Park Centre, Low Street, Sherburn in Elmet | 27/10/2015 | 05/11/2015 | . | 08/02/2016 | N/A | 1 Serious 1 Slight | 0 | 30 |  |  |  |  | TBC
SE1510190 | SELBY | Moor Lane/ Hagg Lane | Along the length of the road from the boundary into the village. | South Duffield | 01/11/2015 | 05/11/2015 | N/A | 08/02/2016 | N/A | 0 | 0 | 30 | 08/03/2016 - 15/03/2016 Hagg Lane | 20/21 | 26/26 | 31/03/2016 | NFA | 25/04/2016
SE1510200 | SELBY | Fulham Lane | Whitley (From Sheepwash Ln to Booty Ln) | Whitley | 05/10/2015 | 06/11/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
SE1510210 | SELBY | York Road | Cliffe | Cliffe | 30/09/2015 | 06/11/2015 | . | 08/02/2016 | N/A | 0 | 0 | 30 | 30/03/16-06/04/16 | 29/31 | 35/37 | 20/04/16 | TBC
SE1510220 | SELBY | High Street | Between Wain Gap junction and The Nook Junction | South Milford | 24/09/2015 | 06/11/2015 | . | 01/02/2016 | N/A | 0 | 0 | 30 | 15/03/16-22/03/16 | 19/20 | 24 | 19/04/16 | TBC
SE1510230 | SELBY | Ryther Road | Passed 11,12,15 Anson Grove entrance into the village | Cawood, Selby | 08/12/2015 | 08/12/2015 | N/A | 16/12/2015 | N/A | 0 | 0 | 30 | 25/01/2016 - 01/02/2016 | 25/29 | 31/35 | 02/02/2016 | NFA | 25/04/2016
SE1510240 | SELBY | A19, Main Street through Escrick | Between Pasronage hotel and village | Escrick, York | 02/10/2015 | 06/11/2015 | N/A | 08/02/2016 | N/A | 7 Slight 1 Serious | 1 Serious | 40 | 01/03/2016 - 08/03/2016 | 37/36 | 42/41 | 11/03/2016 | NFA | 25/04/2016
SE1510270 | SELBY | Selby Road | Selby Road, Eggborough | Eggborough | 17/09/2015 | 21/09/2015 | N/A | 08/02/2016 | N/A | 2 slight (not speed related) | 0 | 30 | 08/03/2016 - 15/03/2016 | 16/18 | 20/21 | 31/03/2016 | NFA | 25/04/2016
SE1510290 | SELBY | B1223 Ulleskelf to Cawood | Ryther | Ryther, Tadcaster | 30/01/2015 | 12/01/2016 - Mr Murray (unsure when others acknowledged as from LA) | . | 09/02/2016 | N/A | 0 | 0 | 30 | Redeployment - incorrect dates showing |  |  |  | TBC
SE1510300 | SELBY | East Common Lane | East Common Lane, Selby | Selby | 02/07/2015 | 03/07/2015 | . | 03/02/2016 | N/A | 1 slight (not speed related) | 0 | 30 | redployment requested 23/02/16 |  |  |  | TBC
SE1510310 | SELBY | Church Hill | Sherburn in Elmet | Church Hill, Sherburn in Elmet | 10/04/2015 | 16/04/2015 | . | 03/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1510320 | SELBY | York Road | York Road, Riccall | Riccall | 30/04/2015 | 30/04/2015 | N/A | 03/02/2016 | N/A | 0 | 0 | 30 | 01/03/2016 - 08/03/2016 | 22/20 | 25/25 | 11/03/2016 | NFA | 25/04/2016
SE1510330 | SELBY | Barlby Road | Barlby Road, Selby | Barlby, Selby | 05/05/2015 | 28/05/2015 | N/A | 03/02/2016 | N/A | 7 slight ( 6 not speed related) | 1 | 30 | 01/03/2016 - 08/03/2016 | 34/34 | 40/40 | 11/03/2016 | ENGINEERING | 25/04/2016
SE1510360 | SELBY | Cat Lane | Bilbrough | Bilbrough | 19/03/2013 | 26/03/2013 | . | 21/01/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1510370 | SELBY | Red Hill Lane | Bilbrough | Bilbrough | 19/03/2013 | 26/03/2013 | . | 21/01/2016 | N/A | 3 slight (not speed related) | 0 | 30 |  |  |  |  | TBC
SE1520160 | SELBY | Park Lane | Park Lane on the straight and Park Road near the school | Barlow, Selby | 20/10/2015 | 05/11/2015 | . | 16/12/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1610171 | SELBY | A63 Hull Road | Near railway bridge | Cliffe | 14/04/2016 | 18/04/2016 | YES - LIVE SITE | N/A | N/A | 0 | 0 | 40 | N/A | N/A | N/A | N/A | NFA
SE1610340 | SELBY | Fox Lane | Thorpe Willoughby | Thorpe Willoughby | 21/08/2015 |  | . | 04/02/2016 | N/A | 1 slight (not speed related) | 0 | 30 | 30/03/16-06/04/16 | 31/31 | 37/37 | 20/04/16 | TBC
SE1610420 | SELBY | A19 | Near to Escrick Business Park | Escrick, York | 27/01/2016 | 02/02/2016 | . | N/A | 21/04/16 | 1 slight ( not speed related) | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
SE1610430 | SELBY | Stuart Grove | Stuart Grove, Eggborough | Eggborough | 05/02/2016 | 05/02/2016 | N/A | 24/02/2016 | N/A | 0 | 0 | 30 | 08/03/2016 - 15/03/2016 | 11/11 | 14/13 | 31/03/2016 | NFA | 25/04/2016
SE1610440 | SELBY | Water Lane, Monk Fryston | Between the School and A63 | Monk Fryston | 05/02/2016 | 08/02/2016 | . | 02/03/2016 | N/A | 0 | 0 | 30 | 18/03/16-24/03/16 | 33/33 | 39/40 | 25/04/16 | TBC
SE1610450 | SELBY | Byram Park Road | OneStop towards farm | Brotherton | 09/02/2016 | 10/02/2016 | . | 08/03/2016 | N/A | 0 | 0 | 30 | 30/03/16-06/04/16 | 20/21 | 26/27 | 20/04/16 | TBC
SE1610460 | SELBY | Back Lane | Riccall | Riccall | 16/02/2016 | 16/02/2016 | N/A | N/A | N/A | 0 | 0 | 30 | N/A | N/A | N/A | N/A | NFA | 23/02/2016
SE1610470 | SELBY | Nanny Lane | Near 2 Fern Cottages near Hall lane | Church Fenton (Tadcaster) | 12/02/2016 | 16/02/2016 | . | 16/03/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1610480 | SELBY | Sand Lane | Near Sand Lane stores | South Milford | 24/02/2016 | 26/02/2016 (Recently investigated) | N/A | N/A | N/A | 0 | 0 | 30 | N/A | N/A | N/A | N/A | NFA
SE1610490 | SELBY | Main Street | All along Main Street (A63) from entry to the village up until the exit out towards South Milford. | Monk Fryston | 12/03/2016 | 15/03/2016 | . | 07/04/2016 | N/A | 1 Slight | 0 | 30 |  |  |  |  | TBC
SE1610500 | SELBY | Main Road, Drax | From the roundabout to Corner Farm | Drax, Selby | 15/03/2016 | 15/03/2016 | . | 07/04/2016 | N/A | 0 | 0 | 30 | 04/05/16-11/05/16 | 24/25 | 30/30 | 12/05/2016 | TBC
SE1610510 | SELBY | Oxton Lane | From the junction of Grange Road to Oxton Drive | Tadcaster | 15/03/2016 | 15/03/2016 | . | 21/04/2016 | N/A | 1 Serious & 1 Slight | 1 Serious | [5 empty] | TBC
SE1610520 | SELBY | A19 Selby Road, Whitley | Outside 2 Blackthorn Close | Whitley | 15/03/2016 | 16/03/2016 |  | 21/04/2016 | N/A | 1 Slight | 0 | 30
SE1610530 | SELBY | Hillam Lane | From the start of the village,(Burton Salmon end), along Hillam Lane to The Cross Keys pub. | Hillam | 21/03/2016 | 22/03/2016 | . | 21/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1610540 | SELBY | York Road | Elvington | Elvington, York | 25/03/2016 | 30/03/2016 | . | 25/04/2016 | N/A | 2 serious & 2 slight | 0 | 30 |  |  |  |  | TBC
SE1610550 | SELBY | Queens Gardens Tadcaster | Full length of Queens Gardens and access to Magnet Sports Club/fitness suite/ Heinekin car park. | Tadcaster | 31/03/2016 | 04/04/2016 | . | 21/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
SE1610560 | SELBY | Common Road | Between Barkston Ash and Church Fenton | Tadcaster | 10/04/2016 | 11/04/2016 | N/A | N/A | 21/04/2016 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
SE1610570 | SELBY | Betteras Hill Road | Village end near railway crossing | Hambleton, Selby | 16/04/2016 | 18/04/2016 | N/A | N/A | 18/04/16 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
SE1610590 | SELBY | Kellington Lane | Goole | Eggborough, Goole | 12/04/2016 | 22/04/2016 | . | 29/04/2016 | N/A | 2 slight | 0 | 30 |  |  |  |  | TBC
SE1610600 | SELBY | Low Street | Swan Hotel to BP Garage | South Milford | 27/04/2016 | 27/04/2016 | . | 05/05/2016 | N/A | 1 Slight -not speed related | 0 | [5 empty] | TBC
SE1610610 | SELBY | Selby Road, Wistow | Along Selby Road by 1 The Homestead | Selby Road, Wistow | 04/05/2016 | 05/05/2016 | . | 12/05/2016 | N/A |  |  | 30 |  |  |  |  | TBC
SE1610620 | SELBY | Main Street | Beal | Beal | 05/05/2016 | 06/05/2016 | . | 12/05/2016 | N/A |  |  | 30 |  |  |  |  | TBC
SE1610630 | SELBY | Skipwith Road | Escrick | Escrick, York | 09/05/2016 | 11/05/2016 | N/A |  | N/A | [7 empty] | TBC
YK1310480 | YORK | Broadway | Fulford | Fulford | 21/11/2013 | 23/12/2013 | N/A | 01/11/2015 | N/A | 6 Slight (not speed related) from Junc FUlford road to Junc Smith Close | 0 | 30 | 13/11/2015 - 23/11/2015 | 28/25 | 34/32 | 16/12/2015 | SID/CSW | 24/02/2016
YK1310520 | YORK | Muncastergate | Malton Road | York | 26/07/2013 | 29/07/2013 | N/A | 21/01/2016 | N/A | 0 | 0 | 30 | 22/01/2016 - 29/01/2016 | 16/17 | 23/24 | 02/02/2016 | NFA | 24/02/2016
YK1310540 | YORK | Appleton Road | Bishopthorpe | Bishopthorpe | 19/11/2013 | 23/12/2013 | . | 21/01/2016 | N/A | 4 Slight (3 not speed related) | 1 | 30 |  |  |  |  | TBC
YK1410310 | YORK | Main Street | Askham Bryan | Askham Bryan | 04/08/2014 | 14/08/2014 | . | 23/02/16 | N/A | 1 Slight ( at the very end of the village on the bend-not speed related) | 0 | 30 |  |  |  |  | TBC
YK1410320 | YORK | A59 Boroughbridge Road | Poppleton | York | 15/09/2014 | 03/10/2014 | . | 21/01/2016 - Redeploment requested 26/04/2016 | N/A | 5 Slight ( roundabout by Elm Bank to park and ride poppleton) | 1 | 30 into 40 | 17/02/16-24/02/16 -Gail sent others 07-15/15 | 29/28 - (Gail's 23/31) | 34/33 - (Gail's 28/37) | 29/02/16 | TBC
YK1410470 | YORK | Main Street | Knapton | Knapton | 27/05/2014 | 27/05/2014 | . | 01/12/2015 | N/A | 0 | 0 | 30 | 08/12/2015 - 15/12/2015 | 24/24 | 33/30 | 16/12/2015 | TBC
YK1410490 | YORK | Leeman Road | York | York | 04/09/2014 | 04/09/2014 | . | 21/01/2016 | N/A | 6 slight 1 serious (not speed related) | 0 | 30 | 25/01/2016 - 01/02/2016 | 29/27 | 34/31 | 02/02/2016 | TBC
YK1410491 | YORK | Leeman Road | Outside Railway Museum | York | 30/01/2016 | 30/01/2016 | . | 05/01/2016 | N/A | 6 slight, 1 serious (not speed related) | 0 | 30 | 10/02/16-17/02/16 | 29/32 | 34/38 | 24/02/2016 | TBC
YK1410500 | YORK | Stirling Road | Clifton Moor | York | 10/11/2014 | 10/11/2014 | AWAITING SITE REVIEW | 21/01/2016 | N/A | 3 slight 1 serious | 0 | 30 | 03/02/2016 - 10/02/2016 | 32/32 | 37/38 | 11/02/2016 | ENFORCEMENT | 26/02/2016
YK1410510 | YORK | Common Road | Dunnington | Dunnington | 04/08/2014 | 14/08/2014 | . | 02/02/2016 Redeployment | N/A | 0 | 0 | 20 | 04/05/16-11/05/16 | 21/17 | 27/21 | 12/05/2016 | TBC
YK1410530 | YORK | Thanet Road | York | York | 04/08/2014 | 14/08/2014 | . | 21/01/2016 | N/A | 8 slight (not speed related) | 0 | 30 | 17/02/16-24/02/16 | 28/27 | 33/32 | 29/01/16 | TBC
YK1410550 | YORK | Heslington Lane | Fulford | Fulford, York | 16/01/2014 | 17/01/2014 | N/A | 01/11/2015 | N/A | 2 slight (not speed related) | 0 | 20 | 13/11/2015 - 23/11/2015 | 22/21 | 27/26 | 16/12/2015 | SID/CSW | 26/02/2016
YK1410560 | YORK | Holly Tree Lane | Dunnington | Dunnington | 03/06/2014 | 05/06/2014 | . | 02/02/2016 Redeployment | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1410570 | YORK | Heworth Green | York | York | 02/12/2014 | 17/12/2014 | . | 21/01/2016 | N/A | 14 slight 1 serious ( 13 slight and 1 serious not speed related) | 1 Slight | 30 | 16/03/16-23/03/16 | 31/31 | 36/35 | 20/04/16 | TBC
YK1410580 | YORK | Barons Crescent | Copmanthorpe | York | 18/09/2014 | 13/10/2014 | . | 21/01/2016 | N/A | 0 | 0 | 30 | 09/03/2016 - 16/03/2016 | 13/14 | 16/17 | 18/03/2016 | TBC
YK1410590 | YORK | A19 Bootham | Bootham | York | 18/11/2014 | 20/11/2014 | N/A | 21/01/2016 | N/A | 6 slight (from Tower to junc St Olaves Rd) Not speed related | 0 | 30 | 03/02/2016 - 10/02/2016 | 28/27 | 34/34 | 11/02/2016 | NFA | 24/02/2016
YK1410600 | YORK | Durlston Drive | Strensall | Strensall | 23/11/2014 | 17/12/2014 | . | 21/01/2016 Redeploy requested 22/02/16 Dates wrong | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510010 | YORK | North Lane | Huntington, York | Huntington, York | 31/03/2015 | 08/04/2015 | N/A | 31/03/2015 | N/A | 1 Slight | 1 Slight | 30 | 12/11/2015-16/11/2015 | 21/20 | 28/28 | 01/12/2015 | NFA | 24/02/2016
YK1510020 | YORK | New Lane | New Lane, Huntington | Huntington, York | 31/03/2015 |  | N/A | 30/04/2015 | N/A | 0 ( from junc of Brecks Lane to Jockey Lane) past cpmps house | 0 | 30 | 12/11/15 - 19/11/15 | 26/26 | 29/29 | 01/12/2015 | SID/CSW | 24/02/2016
YK1510030 | YORK | Wetherby Road | Wetherby Road, Rufforth | Rufforth, York | 30/03/2015 | 31/03/2015 | . | Redeployment 27/01/2016 | N/A | 1 Slight | 0 | 30 | 22/01/2016 - 29/01/2016 | 33/32 | 37/37 | 02/02/2016 | TBC
YK1510031 | YORK | Wetherby Road, Rufforth | Near Middlewood Close | Rufforth | 30/03/2015 | 31/03/2015 | . | 21/04/2016 | N/A | 1 | 0 | 30 | 30/03/16-06/04/16 | 21/20 | 24/23 | 21/04/16 | TBC
YK1510040 | YORK | Bradley Lane | Rufforth, York | Rufforth, York | 16/02/2015 | 19/02/2015 | . | 21/01/2016 | N/A | 0 | 0 | 30 | 16/03/16-23/03/16 | 33/35 | 41 | 19/04/16 | TBC
YK1510050 | YORK | A1036 Malton Road | Malton Road, York, near Hewarth Golf Club | York | 16/02/2015 | 19/02/2015 | . | 27/01/2016- Recieved data back with wrong dates (2015 data on box?) returned for enquiry and possible re deployment | N/A | 2 Slight | 0 | 40 | 22/03/16-29/03/16 | 25/27 | 30/30 | 20/04/16 | TBC
YK1510060 | YORK | Gale Lane | Gale Lane, York | Acomb, York | 26/05/2015 online - 11/11/15 | 02/07/2015 | . | 04/02/2016 | N/A | 15 Slight | 0 | 20 |  |  |  |  | TBC
YK1510070 | YORK | Haxby Road | Haxby Road, New Earswick, York | New Earswick, York | 18/08/2015 | 20/08/2015 | . | 25/01/2016 | N/A | 8 Slight 1 serious in the New Earswick village area | 1 Slight | 30 | 22/0316-29/03/16 (this is a redployment) | 23/24 | 28/29 | 20/04/16 | TBC
YK1510080 | YORK | York Road | From R/A Near QE barracks. Lengh of York road To jnt of Westend rd, Strensall | Strensall, York | 03/07/2015 | 10/10/2015 | . | 05/02/2016 | N/A | 2 Slight | 0 | 30 |  |  |  |  | TBC
YK1510090 | YORK | Murton Lane | Murton Lane, Murton | Murton, York | 17/09/2015 | 18/09/2015 | . | 05/02/2016 | N/A | 0 | 0 | 40 |  |  |  |  | TBC
YK1510100 | YORK | Scarcroft Road | Scarcroft Road, York | York | 08/06/2015 | 09/06/2015 | N/A | 09/06/2015 | N/A | 7 Slight 2 Serious | 0 | 20 | N/A | N/A | N/A | N/A | NFA | 16/11/2015
YK1510110 | YORK | Grantham Drive | Grantham Drive, York | York | 12/06/2015 | 07/07/2015 | . | 04/02/2016 | N/A | 1 Slight | 0 | 20 |  |  |  |  | TBC
YK1510120 | YORK | Chaloners Road | Chaloners Road, Dringhouses | Dringhouses, York | 08/06/2015 | 09/06/2015 | . | 04/02/2016 | N/A | 1 Slight 1 Serious | 0 | 30 |  |  |  |  | TBC
YK1510130 | YORK | Pulleyn Drive | Pulleyn Drive, Tadcaster Road | Tadcaster Road, York | 30/01/2015 | 30/01/2015 | . | 21/01/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510140 | YORK | The Old Village | The Old Village, Huntington | Huntington, York | 03/03/2015 | 09/03/2015 | . | 02/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510150 | YORK | Northfield Lane | Northfield Lane, Upper Poppleton | Upper Poppleton, York | 07/08/2015 | 07/08/2015 | N/A | N/A | 21/04/16 | 0 | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
YK1510160 | YORK | Main Street | Main Street, Hessay | Hessay, York | 08/06/2015 |  | . | 04/02/2016 | N/A | 1 Slight | 0 | 30 |  |  |  |  | TBC
YK1510170 | YORK | New Road | New Road, Hessay | Hessay, York | 08/06/2015 |  | . | 04/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510180 | YORK | Cranbrook Road | Cranbrook Road, Acomb | Acomb, York | 15/07/2015 |  | . | 05/02/2016 - Redeployment requested 29/04/16 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510190 | YORK | Grants Avenue | Grants Avenue, Fulford | Selby | 29/07/2015 | 04/08/2015 | N/A | 08/12/2015 | N/A | 0 | 0 | 20 | 06/01/2016-13/01/2016 | 19/19 | 26/25 | 14/01/2016 | ENGINEERING | 26/02/2016
YK1510200 | YORK | Heworth Road | Heworth Road, Heworth | Heworth, York | 14/08/2015 | 17/08/2015 | N/A | 12/11/2015 | N/A | 0 | 0 | 20 | June 2015 | 22/22 | 26/27 | 01/12/2016 | NFA | 26/02/2016
YK1510210 | YORK | Willow Bank | Willow Bank, New Earswick | New Earswick, York | 18/08/2015 | 20/08/2015 | . | 05/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510220 | YORK | A166 Stamford Bridge Road | Stamford Bridge Road, near the Balloon Tree farmshop | York | 17/09/2015 | 18/09/2015 | . | 05/02/2016 | N/A | 5 Slight 1 Serious | 0 | 40 |  |  |  |  | TBC
YK1510230 | YORK | St Saviourgate | St Saviourgate | York | 17/09/2015 | 21/09/2015 | . | 05/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510240 | YORK | Jockey Lane | Jockey Lane, Huntington | York | 04/08/2015 | 04/08/2015 | . | Redeployment 27/01/2016 | N/A | 5 Slight | 1 | 30 | 30/03/16-06/04/16 | 19/20 | 23 | 20/04/16 | TBC
YK1510250 | YORK | Beckfield Lane | Acomb end 20mph zone nr Sainsburys & All of street | York | 29/10/2015 | 05/11/2015 | . | 2015 | N/A | 5 Slight | 0 | 30 | 13/11/2015 - 23/11/2015 | 26/28 | 31/32 | 20/01/2016 | TBC
YK1510270 | YORK | Second Avenue | East Parade Junction | York | 07/10/2015 | 05/11/2015 | . | 05/02/2016 | N/A | 1 Slight | 0 | 30 |  |  |  |  | TBC
YK1510280 | YORK | Hallcroft Lane | Nr no. 7 | Copmanthorpe, York | 06/10/2015 | 06/11/2015 | . | Redeployment 27/01/2016 | N/A | 1 Slight near address 1 Fatal at junction of Manor Heath | 0 | 30 |  |  |  |  | TBC
YK1510290 | YORK | Moor Lane | Strensall | Strensall, York | 25/09/2015 | 06/11/2015 | . | 05/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510300 | YORK | Tadcaster Road | Tadcaster Road, York | Copmanthorpe, York | 29/09/2015 | 06/11/2015 | . | 29/09/2015 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510320 | YORK | Hopgrove Lane South | Nr Wheeldale Drive | Hopgrove Lane South, York | 04/11/2015 | 06/11/2015 | . | 05/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510330 | YORK | Nunnery Lane | Nunnery Lane, York | York | 10/11/2015 | 10/11/2015 | . | 05/02/2016 | N/A | 7 Slight and 1 Serious | 0 | 30 |  |  |  |  | TBC
YK1510340 | YORK | Acomb Wood Drive | Stretch between Tesco Express and Alness Drive | Acomb, York | 11/11/2015 | 11/11/2015 | . | 08/02/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1510350 | YORK | Millfield Lane | Outside 46 Millfield Lane | Nether Poppleton, York | 11/11/2015 | 11/11/2015 | . | 08/02/2016 | N/A | 1 Slight | 0 | 30 |  |  |  |  | TBC
YK1510360 | YORK | Thoresby Road | From St Stephens Road, Foxwood | York | 11/11/2015 | 11/11/2015 | . | 09/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510370 | YORK | A59 Poppleton Road | Between the Fox pub and Poppleton school | Acomb, York | 11/11/2015 | 11/11/2015 | . | 09/02/2016 | N/A | 9 Slight | 1 Slight | 30 |  |  |  |  | TBC
YK1510380 | YORK | Strensall Road | End of the garden village entrance, Earswick | Earswick, York | 11/11/2015 | 11/11/2015 | . | 09/02/2016 | N/A | 1 Slight | 1 Slight | 30 |  |  |  |  | TBC
YK1510390 | YORK | Hamilton Drive | Junction with Mattison Way (10am-2pm & 7pm-7am) | York | 11/11/2015 | 12/11/2015 | . | 09/02/2016 | N/A | 1 Slight | 0 | 30 |  |  |  |  | TBC
YK1510400 | YORK | Kingsway West | After the bollards at Stuart Road and exiting Ascot Way | York | 11/11/2015 | 12/11/2015 | . | 09/02/2016 | N/A | 3 Slight (not speed related) | 0 | 20 |  |  |  |  | TBC
YK1510410 | YORK | Carr Lane | Between York rd and Boroughbridge rd | Acomb | 11/11/2015 | 12/11/2015 | . | 09/02/2016 | N/A | 8 Slight (not speed related) | 0 | 30 |  |  |  |  | TBC
YK1510420 | YORK | Long Ridge Lane | Long Ridge Lane, Upper Poppleton (8-9am & 3-7pm) Junction of Dikelands Lane | Upper Poppleton, York | 11/11/2015 | 12/11/2015 | . | 09/12/2015 | N/A | 1 Slight | 0 | 30 | 06/01/16 - 13/01/16 | 30/29 | 35/34 | 21/01/2016 | TBC
YK1510430 | YORK | Moorgate | Between Acomb Road and Hamilton Drive (The full length of Moorgate) | Acomb, York | 11/11/2015 | 12/11/2015 | . | 08/02/2016 | N/A | 1 Slight | 0 | 20 |  |  |  |  | TBC
YK1510440 | YORK | A19 Roundabout (All Aproaches) | Shipton Road, Rawcliffe | Rawcliffe, York | 16/11/2015 | 16/11/2015 | . | 05/02/2016 | N/A | 3 Serious and 11 Slight | 0 | 40 |  |  |  |  | TBC
YK1510450 | YORK | Manor Lane | Manor Lane, mainly mini roundabout with Kensington Road | Rawcliffe, York | 16/11/2015 | 16/11/2015 | . | 09/02/2016 | N/A | 3 Slight 1 Serious | 0 | 30 |  |  |  |  | TBC
YK1510460 | YORK | Thirsk Road | Outside The Meadows, Thirsk Road, Easingwold | Easingwold | 07/12/2015 | 07/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 20 | 21/04/2016 - 28/04/2016 | 19/17 | 23/20 | 28/04/2016 | TBC
YK1510610 | YORK | Tisbury Road | Entering Tisbury Road (outside 23), York | York | 30/12/2015 | 30/12/2015 | . | 09/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1510620 | YORK | Bellhouse Way | From Foxwood Lane to Acomb Wood Drive | York | 30/12/2015 | 30/12/2015 | . | 09/02/2016 | N/A | 5 SLight | 0 | 30 |  |  |  |  | TBC
YK1520260 | YORK | Mill Lane, Wigginton | Approach to the zebra crossing in both directions | Wigginton, York | 10/12/2015 | 11/12/2015 | . | 09/02/2016 | N/A | 1 Slight | 1 Slight | 30 |  |  |  |  | TBC
YK1610630 | YORK | Knavesmire Crescent | Knavesmire Crescent between Campleshon Road and 48 Knavesmire Crescent. | York | 04/01/2016 | 08/01/2016 | . | 09/02/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1610650 | YORK | Askham Fields Lane | College to Main Street | Askham Bryan | 29/01/2016 | 29/01/2016 | . | N/A | 06/05/2016 | 1 Slight (not speed related) | 0 | 60 | N/A | N/A | N/A | N/A | 60-Back to Highways
YK1610660 | YORK | Main Street | Fulford | Not Given | 19/01/2016 | 29/01/2016 | . | 17/02/2016 | N/A | 2 slight (not speed related) | 0 | 30 |  |  |  |  | TBC
YK1610670 | YORK | Green Lane | Lower 2/3 of Road, Acomb | Acomb, York | 03/02/2016 | 04/02/2016 | N/A | 07/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1610680 | YORK | Arlington Road | Whole length of Arlington Road, York | York | 17/02/2016 | 17/02/2016 | . | 16/03/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1610690 | YORK | A19 Crockey Hill | AKA Selby Road. Passed Lodge Cottage & Streawberry Fields Cafe | York | 24/02/2016 | 26/02/2016 | . | 16/03/2016 | N/A | 10 slight 1 serious (0 speed related) | 0 | 40 from Wheldrake to Lodge Cottage- Then into 60 |  |  |  |  | TBC
YK1610700 | YORK | St John's Walk | Near 1 Musgrave House | St John's Walk, York | 13/03/2016 | 15/03/2016 | . | 25/04/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1610710 | YORK | Howard Link | Outside 14 Howard Link, York | York | 24/03/2016 | 24/03/2016 | . | 25/04/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1610720 | YORK | Bransholme Drive | To the junction of Redmires Close | Clifton Moor, York | 24/03/2016 | 24/03/2016 | . | 25/04/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1610730 | YORK | Wheldrake Lane | Wheldrake Lane B1228 | Elvington, York | 06/04/2016 | 07/04/2016 | . | 26/04/2016 | N/A | 1 serious/1 Slight | 0 | 30 |  |  |  |  | TBC
YK1610740 | YORK | Greenshaw Drive | Haxby | Haxby | 29/03/2016 | 18/04/2016 | . | 26/04/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1610750 | YORK | Heslington Road | Near Bison coffee shop | York | 15/04/2016 | 18/04/2016 | . | 29/04/2016 | N/A | 4 slight | 0 | 20 |  |  |  |  | TBC
YK1610760 | YORK | Whitby Avenue | Junction with Stockton Lane | York | 21/04/2016 | 22/04/2016 | . | 05/05/2016 | N/A | 0 | 0 | 20 |  |  |  |  | TBC
YK1610770 | YORK | Rogers Court | From the new parking area at the back of Rogers Court to the junction with Walker Drive. | Acomb | 25/04/2016 | 26/04/2016 | . | 05/05/2016 | N/A | 0 | 0 | 30 |  |  |  |  | TBC
YK1610780 | YORK | Danebury Drive | whole road | York | 30/04/2016 | 03/05/2016 | . | 12/05/2016 | N/A | 1 Slight not speed related | 0 | 20 |  |  |  |  | TBC